## Summary
Bid Wit Me (BWM) — 3D online Spades — Roadmap
Updated | Oct 11, 2026
Current release | Release 6 + hotfix (live, BETA); Release 7 in progress
Status | Features
Done
In progress
Next
Later
Total
Links
Game | https://bid-wit-me.pages.dev
Server | https://bid-wit-me-server.demetrius-robinson31.workers.dev
Code (private repo) | https://github.com/M33CH1384/bid-wit-me

## Roadmap
Area | Feature | Status | Release | Notes | Date shipped
Rules | Core Spades rules engine (bidding, books, bags, Nil, scoring) with full test suite | Done | Release 1 | Rules checked by automated tests and thousands of simulated games | 2026-10-08
Rules | Joker mode (Big & Little Joker as top trumps, house trump order) | Done | Release 1 |  | 2026-10-08
Rules | Ace Down mode | Done | Release 1 |  | 2026-10-08
Rules | Cutthroat for 3 and 4 players (every player for themselves) | Done | Release 1 | 3-player game removes a card so the deck divides evenly | 2026-10-08
Bots | Computer opponents and partners | Done | Release 1 | Bid and play on their own so you can play solo | 2026-10-08
UI/UX | 3D card table | Done | Release 1 | Real 3D table, cards and camera | 2026-10-08
UI/UX | Streamer-style look (purple & gold overlay, scoreboard bug, BWM branding) | Done | Release 1 |  | 2026-10-08
Audio | Card and table sound effects (deal, play, cut, sweep, win/lose stings) | Done | Release 1 |  | 2026-10-09
Audio | Hip-hop music playlist with binaural-style stereo widening | Done | Release 1 | Shuffled, crossfades between tracks; grew to 17 tracks in Release 4, all volume-matched | 2026-10-09
Gameplay | Game saves and resumes after a page refresh | Done | Release 1 |  | 2026-10-09
Gameplay | Visible shuffle and deal animation | Done | Release 1 |  | 2026-10-09
Online | Online multiplayer: create a table, share an invite link, play with friends | Done | Release 2 | Server runs the rules so nobody can cheat; bots fill empty seats; reconnects after drops | 2026-10-09
Online | Live video and mic bubbles at the table | Done | Release 2 | Optional camera and microphone for each player | 2026-10-09
Online | Reliable moves on bad connections (no doubled or lost plays) | Done | Release 2 | Also cut online data use by about 60% | 2026-10-09
UI/UX | Step-by-step setup wizard | Done | Release 2 |  | 2026-10-09
UI/UX | Landscape phone layout | Done | Release 2 |  | 2026-10-09
UI/UX | Tips for new players | Done | Release 2 | Expanded in Releases 3 and 4 | 2026-10-09
Rules | Blind Nil (cards flip over in place after the bid) | Done | Release 2 |  | 2026-10-09
Rules | First hand: books bid themselves (house rule) | Done | Release 3 | On by default, can be switched off | 2026-10-09
UI/UX | Bid coach (helps count your books and suggests a bid) | Done | Release 3 |  | 2026-10-09
UI/UX | Learning mode (slower game while tips are on) | Done | Release 3 |  | 2026-10-09
Effects | Hype effects: streak pop-ups (Heat Check / On Fire / Unstoppable), SHOT! / GOT SHOT, Joker rumbles, camera shake | Done | Release 3 |  | 2026-10-09
Online | Table Talk between hands (recap, video grid, chat, Ready button) | Done | Release 3 | Host sets the countdown (15 to 45 seconds) | 2026-10-09
Online | Host music shared with the table | Done | Release 3 |  | 2026-10-09
Online | Idle player auto-replace, host kick and vote kick | Done | Release 3 |  | 2026-10-09
UI/UX | Redesigned lobby (chat always visible, phone chat drawer) | Done | Release 3 |  | 2026-10-09
Online | Optional partner mic mute (host setting, during card play only) | Done | Release 4 (0.3.0) | Off by default; partners can always talk during bidding | 2026-10-10
Bots | Random bot names each game (80-name pool) | Done | Release 4 (0.3.0) |  | 2026-10-10
UI/UX | Plain-English tips rewrite + tappable glossary | Done | Release 4 (0.3.0) | Tips point at the cards they talk about | 2026-10-10
UI/UX | Playable cards glow, unplayable cards dim | Done | Release 4 (0.3.0) |  | 2026-10-10
Infra | BETA tag and version stamp | Done | Release 4 (0.3.0) |  | 2026-10-10
Infra | Send feedback form (with screenshot), emailed to Demetrius via Resend | Done | Release 4 (0.3.0) | Includes a private admin page to read feedback | 2026-10-10
Infra | Cash App tip jar | Done | Release 4 (0.3.0) |  | 2026-10-10
Effects | Wheels: team bids 10+ callout and supercar peel-out celebration | Done | Release 4 (0.3.0) |  | 2026-10-10
Audio | Spade cut sound with escalating over-cut callouts | Done | Release 4 (0.3.0) |  | 2026-10-10
Effects | Nuke (Big Joker over Little Joker): cinematic mushroom-cloud blast | Done | Release 4 (0.3.0) | Host picks intensity: Full Nuke / Classic / Off | 2026-10-10
Bots | Bot personalities with trash talk | Done | Release 4 (0.3.0) | Expanded to 19 personalities in Release 5 | 2026-10-10
Online | Team names | Done | Release 4 (0.3.0) |  | 2026-10-10
Gameplay | Rematch series record (who's up in the series) | Done | Release 4 (0.3.0) |  | 2026-10-10
Effects | Last-trick nuke finishes the hand automatically | Done | Release 5 |  | 2026-10-10
Effects | Run it! (claim the rest of the tricks) with tornado finish | Done | Release 5 |  | 2026-10-10
Effects | Storm Chaser badge (for Run it!) | Done | Release 5 |  | 2026-10-10
Bots | Recorded bot voices, male and female | Done | Release 5 | 19 personalities, each in both voices | 2026-10-11
Bots | Bot skill levels: Novice, Regular, Pro, Shark, or Mixed | Done | Release 5 | Smarter bots: count cards, don't waste Jokers, don't trump their partner | 2026-10-11
Bots | Trash talk intensity setting | Done | Release 5 |  | 2026-10-11
Online | Talk trash quick-chat button (ready-made lines) | Done | Release 5 | Includes 'Slow your roll, cowboy!' | 2026-10-11
Rules | Shot = out (getting shot ends the game) | Done | Release 5 | With a first-hand minimum option | 2026-10-11
Rules | Rule lock (game rules can't change mid-game) | Done | Release 5 | Pace and social settings can still change | 2026-10-11
Rules | Dealer rotation carries over into rematches | Done | Release 5 |  | 2026-10-11
UI/UX | DEALER and ON NOTICE chips on player plates | Done | Release 5 |  | 2026-10-11
Effects | Spade callouts and streak hype | Done | Release 5 | Built across Releases 3 to 5 | 2026-10-11
Rules | Team bid order (non-dealing team bids first, dealer last) | Done | Release 6 | Cutthroat still bids clockwise | 2026-10-11
Online | Public partner talk during bidding (all chat is public) | Done | Release 6 | Partner talk presets like '3-ish' and 'I'm weak'; bot partners say their count | 2026-10-11
UI/UX | Score pad redesign (hand-by-hand bid, took, points, bags) | Done | Release 6 |  | 2026-10-11
Rules | Cutthroat options: minimum bid, Nil, Blind Nil, bags toggles | Done | Release 6 | 3-player removes the lowest non-spade card | 2026-10-11
Gameplay | Hand-end pacing (waits for every celebration to finish) | Done | Release 6 |  | 2026-10-11
Infra | Faster first load (27 s down to 5-8 s on a slow phone) | Done | Release 6 |  | 2026-10-11
Online | Victory video spotlight (winners front and center) | Done | Release 6 |  | 2026-10-11
UI/UX | Phone setup fixes (wizard fits small screens) | Done | Release 6 |  | 2026-10-11
Infra | Private GitHub repo | Done | Release 6 | github.com/M33CH1384/bid-wit-me
Effects | Hotfix: Run it! effects work online | Done | Release 6 hotfix |  | 2026-10-11
Bots | Hotfix: bot lines match the bot's gender (mama/papa, IS HIM/HER, etc.) | Done | Release 6 hotfix | Text and recorded clips | 2026-10-11
Audio | Hotfix: redesigned sound sheet (sections, big sliders) | Done | Release 6 hotfix |  | 2026-10-11
Audio | Hotfix: host music plays in the lobby and setup | Done | Release 6 hotfix |  | 2026-10-11
UI/UX | Hotfix: player plates no longer overlap cards or video | Done | Release 6 hotfix | Also clearer scoreboard on phones and card art fixes | 2026-10-11
Gameplay | 10 venues/arenas: Backyard Cookout, Mansion, Barbershop, Church Basement, Rooftop, Speakeasy Lounge, Vegas High Roller, Beach Cabana, Grandma's Kitchen, Yacht Deck | In progress | Release 7 | Work started Oct 11
UI/UX | Victory headline grammar ('YOU WIN') | In progress | Release 7
Accounts | Sign-in and accounts plan | In progress | Release 7 | Plan written: security hardening first, then optional sign-in; guest play stays the default
Effects | Nuke countdown (Big Joker pulses until the trick finishes, then nuke) | Next
Accounts | Social logins: Google, Discord, X, Facebook, email | Next |  | Apple later (needs $99/yr Apple developer account)
Accounts | Usernames | Next
Online | Global and local leaderboards | Next
Online | Scheduled tournaments (bracket or Swiss, host picks) | Next
Online | Friends list + play again | Next
Accounts | Team names saved to profiles | Next
Accounts | Rematch head-to-head history in profiles | Next
Accounts | Player stats + skill rating (bid accuracy, speed, partnerships, Best duos) | Later
Accounts | Badges (Sharpshooter, Wheels, Nil Boss, Storm Chaser, etc.) | Later |  | Storm Chaser already exists on-device
Audio | More host music polish | Later
Infra | Native apps (iPhone / Android) | Later

## Release log
Release | Date | Highlights
Release 1 | Oct 8–9, 2026 | Rules engine (Joker, Ace Down, Cutthroat), bots, 3D table, purple & gold streamer look, sound effects, hip-hop playlist, save & resume, first deploy
Release 2 | Oct 9, 2026 | Online multiplayer with invite links and video/mic bubbles, setup wizard, landscape layout, new-player tips, sound controls, Blind Nil card flip, steadier online play
Release 3 | Oct 9, 2026 | First hand books bid themselves, bid coach, learning mode, hype effects, Table Talk between hands, host music, idle auto-replace / kick / vote kick, new lobby
Release 4 (0.3.0) | Oct 10, 2026 | BETA tag, feedback form (emailed via Resend), Cash App tip jar, Wheels, cinematic nuke with intensity setting, bot personalities + trash talk, team names, rematch series, 17-track playlist, plain-English tips + glossary
Release 5 | Oct 10–11, 2026 | Run it! with tornado + Storm Chaser badge, last-trick nuke, recorded male/female bot voices (19 personalities), bot skill levels, trash talk intensity, Shot = out, rule lock, dealer rotation in rematches, Talk trash quick chat
Release 6 | Oct 11, 2026 | Team bid order, public partner talk during bidding, score pad redesign, Cutthroat options, hand-end pacing, much faster first load, victory video spotlight, phone setup fixes
Release 6 hotfix | Oct 11, 2026 | Run it! effects online, gendered bot lines, new sound sheet, host music in lobby/setup, player plates no longer overlap cards or video, clearer phone scoreboard
Release 7 (in progress) | Started Oct 11, 2026 | 10 venues/arenas, 'YOU WIN' headline fix, sign-in & accounts plan